## Sheet1
|  |  | BOQ3 |  | USD = USD Dollar, IDR = Rupiah
Work ID | Work Name | Product ID | Material Name | Uom | Spec | QTY | Unit Price | Total Price | Currency | CFS Kode | Cfs Nama | Days
0 | Services for Transport | 820004-0000 | Transport Material - Tower | trip |  | 20 | 15500000 | 310000000 | IDR | 302 | Materials Transportation | 7
2034 | Services for feneral elektrical work | 129098-0000 | Pekerjaan Erection Transmission Line Steel Pole | kg |  | 32769 | 1500 | 49153500 | IDR | 301 | M/E + Steel services | 42
2034 | Services for feneral elektrical work | 323051-0000 | Pemasangan Conductor TAL 660 mm2 | meter |  | 1104 | 75000 | 82800000 | IDR | 301 | M/E + Steel services | 42
2034 | Services for feneral elektrical work | 323053-0000 | Set of clamps, connectors and accessories | set |  | 84 | 250000 | 21000000 | IDR | 301 | M/E + Steel services | 42
2034 | Services for feneral elektrical work | 323054-0000 | Conductor GSW 55 mm2 | meter |  | 400 | 35000 | 14000000 | IDR | 301 | M/E + Steel services | 42
2034 | Services for feneral elektrical work | 323069-0000 | Pemasangan 150 kV 3 Phase Disconnecting Switch motor operated, 31.5 kA 2000 A without Earthing switch, complete with clamps and supporting structure for IBT bay | Set |  | 4 | 4500000 | 18000000 | IDR | 301 | M/E + Steel services | 5
2031 | Services for engineering design | 323069-0000 | Pemasangan 150 kV 3 Phase Disconnecting Switch motor operated, 31.5 kA 2000 A without Earthing switch, complete with clamps and supporting structure for IBT bay | Set |  | 2 | 4500000 | 9000000 | IDR | 301 | M/E + Steel services | 5
2034 | Services for feneral elektrical work | 323070-0000 | Pemasangan 150 kV 3 Phase SF6 Circuit Breaker 40 kA 3150 A, complete with clamps and supporting structure for IBT bay | Set |  | 2 | 4500000 | 9000000 | IDR | 301 | M/E + Steel services | 5
2034 | Services for feneral elektrical work | 323076-0000 | Jasa 150 kV Current Transformer for Bus-Coupler Bay complete with clamps and supporting structure comprising, Core 1, 1000-2000/1 A, Class X for Main Busbar Protection | Set |  | 6 | 4500000 | 27000000 | IDR | 301 | M/E + Steel services | 5
2031 | Services for engineering design | 323076-0000 | Jasa 150 kV Current Transformer for Bus-Coupler Bay complete with clamps and supporting structure comprising, Core 1, 1000-2000/1 A, Class X for Main Busbar Protection | set |  | 12 | 4500000 | 54000000 | IDR | 301 | M/E + Steel services | 5
2034 | Services for feneral elektrical work | 323063-0000 | 150 kV Capacitor Voltage Transformer with 2 secondary winding, ratio 150000V.V3 / 100V.V3 / 100V.V3, Burden 100 VA Cl 0.2, 150 VA CL 3P, min. capacitance 10000 PF complete with clamps, supporting structure | set |  | 6 | 4500000 | 27000000 | IDR | 301 | M/E + Steel services | 5
2034 | Services for feneral elektrical work | 323200-0000 | PEMASANGAN - Lightning Arrester 150 kV, 20 kA with creepage distance 31 mm/kV for Line bay | set |  | 6 | 4500000 | 27000000 | IDR | 301 | M/E + Steel services | 3
2034 | Services for feneral elektrical work | 323201-0000 | PEMASANGAN - 150 kV Single phase XLPE Power Cable CU 3 x 2 x 1000 mm2/ph complete | meter |  | 2400 | 75000 | 180000000 | IDR | 301 | M/E + Steel services | 30
2034 | Services for feneral elektrical work | 323202-0000 | PEMASANGAN - 150 kV single phase cable sealing end complete | set |  | 24 | 2500000 | 60000000 | IDR | 301 | M/E + Steel services | 30
2034 | Services for feneral elektrical work | 323080-0000 | Jasa Marshalling kiosks for Bus Coupler bay | set |  | 2 | 4500000 | 9000000 | IDR | 301 | M/E + Steel services | 3
2001 | Prepartaion Work | 129137-0000 | Mobilisasi-Demobilisasi | ls |  | 1 | 9375000 | 9375000 | IDR | 203 | Civil works
1023 | Material for common civil work | 129259-0000 | PEKERJAAN PRASARANA DAN SWITCHYARDMembuat Papan nama proyek | unit |  | 1 | 530204.5 | 530204.5 | IDR | 203 | Civil works | 1
1023 | Material for common civil work | 129120-0000 | Bouwplank | m |  | 276 | 29128.125 | 8039362.5 | IDR | 203 | Civil works | 3
1023 | Material for common civil work | 111272-000 | Pembuatan Pagar Pengaman dari Pasangan Batu | m |  | 200 | 35000 | 7000000 | IDR | 203 | Civil works | 7
1023 | Material for common civil work | 111271-000 | Pompa Air Kerja (termasuk instalasi) | ls |  | 1 | 759375 | 759375 | IDR | 203 | Civil works | 3
1023 | Material for common civil work | 129328-000 | Biaya air dan Listrik | ls |  | 1 | 18750000 | 18750000 | IDR | 203 | Civil works | 1
1023 | Material for common civil work | 129022-000 | Soil investigation (sondir) in tower location | pcs |  | 3 | 1300000 | 3900000 | IDR | 203 | Civil works | 1
1023 | Material for common civil work | 129121-0000 | Soil test investigation for switchyard SPT, DCPT, Core Drilling and Test Lab | pcs |  | 1 | 900000 | 900000 | IDR | 203 | Civil works | 1
1023 | Material for common civil work | 111338-000 | Soil test (SPT,DCPT, Coredrilling, Test Lab) and report | set |  | 5 | 500000 | 2500000 | IDR | 203 | Civil works | 7
1023 | Material for common civil work | 129117-0000 | Site Clearing | m2 |  | 1568 | 14238.2812 | 22325625 | IDR | 203 | Civil works | 7
1023 | Material for common civil work | 129118-0000 | Common Excavation | m3 |  | 368.8 | 53000 | 19546400 | IDR | 203 | Civil works | 7
1023 | Material for common civil work | 129131-000 | Pembuangan Tanah Keluar Lokasi | m3 |  | 368.8 | 32109.375 | 11841937.5 | IDR | 203 | Civil works | 7
1023 | Material for common civil work | 129119-0000 | Back fill with selected material | m3 |  | 295.04 | 52734.375 | 15558750 | IDR | 203 | Civil works | 7
1023 | Material for common civil work | 111284-000 | SubBase Coarse Agregat Class-A | m3 |  | 336 | 40500 | 13608000 | IDR | 203 | Civil works | 21
1023 | Material for common civil work | 111329-000 | Base structure (Sub base & Base coarse) | m2 |  | 168 | 162000 | 27216000 | IDR | 203 | Civil works | 14
1023 | Material for common civil work | 111330-0000 | 50 mm Asphalt hot mix | m2 |  | 168 | 35000 | 5880000 | IDR | 203 | Civil works | 14
1023 | Material for common civil work | 120000-0000 | Pekerjaan Perkerasan Jalan, Pengaspalan | m2 |  | 168 | 70000 | 11760000 | IDR | 203 | Civil works | 14
1023 | Material for common civil work | 124001-000 | Pekerjaan Membuat Lantai Kerja Beton Tumbuk 1 Pc : 3 Ps : 5 Krl | m3 |  | 8.4 | 886521.4815 | 7446780.4444 | IDR | 203 | Civil works | 8
1023 | Material for common civil work | 124023-000 | Pekerjaan Membuat Beton Bertulang 1Pc,2 Ps,3 Split dengan (125 kg Pembesian) | m3 |  | 20.16 | 1091644.4444 | 22007551.9999 | IDR | 203 | Civil works | 3
1023 | Material for common civil work | 323203-0000 | Joint Sealing & Joint Filler (4 mm) | m |  | 56 | 75000 | 4200000 | IDR | 203 | Civil works | 5
1024 | Material for common Mechanical work | 111331-0000 | Kerbs (15x30x50cm) | m |  | 107.8 | 310500 | 33471900 | IDR | 203 | Civil works | 45
1023 | Material for common civil work | 111331-0000 | Kerbs (15x30x50cm) | m |  | 168 | 310500 | 52164000 | IDR | 203 | Civil works | 60
1023 | Material for common civil work | 111478-0000 | BRC Fence 1.50 m height | m |  | 60 | 1100000 | 66000000 | IDR | 203 | Civil works | 40
1023 | Material for common civil work | 111350-000 | Pintu pagar BRC | unit |  | 1 | 6000000 | 6000000 | IDR | 203 | Civil works | 20
1023 | Material for common civil work | 111333-0000 | Gravel (dia 3 - 5 cm), tebal 15 cm | m3 |  | 940.8 | 51600 | 48545280 | IDR | 203 | Civil works | 60
1023 | Material for common civil work | 122012-000 | Pekerjaan Urugan Pasir | m3 |  | 58.8 | 270000 | 15876000 | IDR | 203 | Civil works | 21
1023 | Material for common civil work | 111334-0000 | Cable trench type I (large) | m' |  | 28 | 1400000 | 39200000 | IDR | 203 | Civil works | 21
1023 | Material for common civil work | 111335-0000 | Cable trench type 2 (medium) | m' |  | 28 | 1200000 | 33600000 | IDR | 203 | Civil works | 14
1024 | Material for common Mechanical work | 111336-0000 | Cable trench type 3 (small) | m' |  | 84 | 1000000 | 84000000 | IDR | 203 | Civil works | 21
1023 | Material for common civil work | 111336-0000 | Cable trench type 3 (for additional gantry) (small, width < 60 cm ) | m' |  | 80 | 1000000 | 80000000 | IDR | 203 | Civil works | 21
1023 | Material for common civil work | 111479-000 | open drainage stone masonry 40x70cm | m' |  | 56 | 394119.1125 | 22070670.3 | IDR | 203 | Civil works | 28
1023 | Material for common civil work | 111340-0000 | Sub soil Drainage dia 30 including gravel & Palm fibre | m' |  | 42 | 595207.0312 | 24998695.3125 | IDR | 203 | Civil works | 30
1023 | Material for common civil work | 111480-0000 | control box 60x60cm | unit |  | 2 | 635162.0625 | 1270324.125 | IDR | 203 | Civil works | 12
1023 | Material for common civil work | 129342-0000 | Excavation and back fill | m3 |  | 94.08 | 53000 | 4986240 | IDR | 203 | Civil works | 10
1023 | Material for common civil work | 313300-0000 | Lightning Arrester | Unit |  | 6 | 5335235.25 | 32011411.5 | IDR | 203 | Civil works | 30
1023 | Material for common civil work | 129332-0000 | Pondasi Capacitor Voltage Transformer | Unit |  | 6 | 5335235.25 | 32011411.5 | IDR | 203 | Civil works | 45
1024 | Material for common Mechanical work | 129333-0000 | Disconnecting Earthing Switches ( 1 set = 3 unit) | Set |  | 2 | 30747348 | 61494696 | IDR | 203 | Civil works | 30
1023 | Material for common civil work | 129333-0000 | Disconnecting Switches ( 1 set = 3 unit) | Set |  | 4 | 30747348 | 122989392 | IDR | 203 | Civil works | 30
1023 | Material for common civil work | 129331-0000 | Pondasi Current Transformer | Unit |  | 6 | 5335235.25 | 32011411.5 | IDR | 203 | Civil works | 30
1023 | Material for common civil work | 211125-0000 | LINE BAY 150kV Three phase Circuit Breaker (3x single phase) | Set |  | 2 | 11022278.25 | 22044556.5 | IDR | 203 | Civil works | 30
1024 | Material for common Mechanical work | 129199-0000 | Post For Gantries TW1 & TW2 (18 m & 13 m) | Unit |  | 7 | 21608130.5 | 151256913.5 | IDR | 203 | Civil works | 45
1023 | Material for common civil work | 129199-0000 | Post For Gantries TW3 (9 m ) | Unit |  | 1 | 21608130.5 | 21608130.5 | IDR | 203 | Civil works | 24
1023 | Material for common civil work | 111481-0000 | pondasi Marshaling Kiosk | Unit |  | 2 | 4391795.25 | 8783590.5 | IDR | 203 | Civil works | 7
1023 | Material for common civil work | 323202-0000 | PEMASANGAN - 150 kV single phase cable sealing end complete | Unit |  | 6 | 5604189.1336 | 33625134.8013 | IDR | 203 | Civil works | 14
1023 | Material for common civil work | 313411-0000 | Light-emitting diode (LED) Street Light 1 x 125 W complete with lighting column 9 m high, fuse box, grounding system and installation of cable conduit and wiring and all accessories and foundation of column (each 50 m length) | NO |  | 2 | 23625000 | 47250000 | IDR | 203 | Civil works | 21
1023 | Material for common civil work | 313412-0000 | Light-emitting diode (LED) Flood Light 1 x 100 W complete with support, fuse box, grounding system and installation of cable conduit and wiring and all accessories for Switchyard | NO |  | 6 | 2156250 | 12937500 | IDR | 203 | Civil works | 21
1023 | Material for common civil work | 111482-0000 | Driven Pile 30 x 30 cm | m' |  | 800 | 50000 | 40000000 | IDR | 203 | Civil works | 24
1023 | Material for common civil work | 129344-0000 | Demolishing of Existing BRC Fence | Ls |  | 1 | 1318325.1 | 1318325.1 | IDR | 203 | Civil works | 5
1023 | Material for common civil work | 129343-0000 | Re-installed of Existing BRC Fence | Ls |  | 1 | 1318325.1 | 1318325.1 | IDR | 203 | Civil works | 5
1023 | Material for common civil work | 129323-000 | Training Multiplexer & PLC | lot |  | 1 | 110911100 | 110911100 | IDR | 301 | M/E + Steel services | 3
1023 | Material for common civil work | 313171-000 | Integrasi including Commisioning SAS eksisting | lot |  | 1 | 827962420 | 827962420 | IDR | 301 | M/E + Steel services | 2
2005 | Services for Finishing | 323204-0000 | FAT - SOGI + SAS | lot |  | 1 | 55821600 | 55821600 | IDR | 301 | M/E + Steel services | 1
2005 | Services for Finishing | 129130-0000 | As Built drawing | Lot |  | 1 | 15000000 | 15000000 | IDR | 301 | M/E + Steel services | 14
Note on G12: ditambah 1 untuk diantara tower Tx -Ty